## Common
1 | Discussion/project
* Use Redmine system during project development
| Target version |  | Description
| <product> ¦ <model> ¦ 000 Question and Review |  | Common information discussion
| <product> ¦ <model> ¦ 000 Question and Review ¦ Code review |  | Discussion related to source code (usualy used in "code review 1" or "code review 2")
| <product> ¦ <model> ¦ 000 Question and Review ¦ Documents review |  | Discussion related to documents (usualy used in "review documents")
| <product> ¦ <model> ¦ 001 Schedule |  | Schedule management (The schedule with .csv format should be uploaded in this target version
| <product> ¦ <model> ¦ 002 Functional Debug |  | Discussion during functional debug
| Subject |  | Description | Order | Example:
| [RVC] |  | Internal ticket (discussion between RVC's members; usualy used in target version is "Question and Review") | 1 |  | [RVC][DNF][CHK][Src] Incorrect connection (dnf.cpp: line 48)
| [<Model_name>] |  | Current project. Here, <Model_name> includes product information (if any) (e.g: "P1M/ECM") | 2 |  | [DNF][QA] Confirm about port list
| [CHK] |  | Ticket for checking document/source code/… Sub-subjects: [<type>[ <version>]] e.g: [CHK][INT v1.0]; [CHK][Src]; [CHK][Data]; …. | 3
| [QA] |  | Ticket for confirmation | 3
2 | Document name
| File | Name | Description
| CFM | CFM-SLD-YY0xx[_<model_name>] | Confirmation file: Used to make clear project request (with customer)
| ISM | ISM-SLD-YY0xx[_<model_name>] | Issue management file: Used to confirm issues during develop project (include take care risk, issue of last projects, ....)
| REQ | REQ-SLD-YY0xx[_<model_name>] | Requirement file
| INT | INT-SLD-YY0xx[_<model_name>] | Internal specification: Used to show design flow
| VRF | VRF-SLD-YY0xx[_<model_name>] | Verification specification: Used to show verification flow
| VRF-01 | VRF-SLD-YY0xx-01[_<model_name>] | Check list: Used to describe test item
| TRA | TRA-SLD-YY0xx[_<model_name>] | Traceability table: Used to show relationship between output documents
| DEV | DEV-SLD-YY0xx[_<model_name>] | Deliverable : Used to manage document version
| INR | INR-SLD-YY0xx[_<model_name>] | Verification report: Used to record verification phase (include: issue/bug information, pass/fail TMs, code line number,...)
| USR | USR-SLD-YY0xx[_<model_name>] | User manual: Used to direct users about using of model
3 | Email
* When you are receiver of an information mail (e.g: header is "Dear <you>"), please reply the email to inform you got that information.
| Subject |  | Description | Order | Example:
| [<group_name>] |  | Ticket of group (should add at the beginning of subject). Here, <group_name> is "SLD" | 1 |  | [SLD][Training][Prj: DNF] Investigation report
| [Training] |  | Ticket for training | 2
| [Prj:<Model_name>] |  | Current project. Here, <Model_name> includes product information (if any) (e.g: "P1M/ECM") | 3
| [CHK] |  | Ticket for checking document/source code/… Sub-subjects: [<type>[ <version>]] e.g: [CHK][INT v1.0]; [CHK][Src]; [CHK][Data]; …. | 4
| [QA] |  | Ticket for confirmation | 4
| [MM] |  | Meeting minutes | 4
| Header |  | Description
| Dear <receiver (s)> |  | Dear list (1st line: for receiver list, 2nd line: for CC list)
CC <other watcher(s)>
| <1 space line> |  | Should separate <Dear list> and <Mail content> by 1 space line
| <Mail content> |  | Write your mail content here
<1 space line>
| <Signature> |  | Your signature (if any)
4 | Windows installation
- Microsoft Visual C++ 2010 Express
- Microsoft Visual Studio 2010 Express
- Python 2.7.3
- VLAB 2.1.2
- GHS\V800.V2013.5.5
5 | Access permission
Please check your access permission as below
| DMS | Documents/1. General Documents/010_ENG/140_FrontEnd/Project/01_SLD/2_SLD_Project/Model_Documents/01_Project_Document_Management
| Redmine | http://172.29.143.164/projects/fe-sld/issues
| Server | ssh rvc-fe01
| Linux location | /shsv/sld
| Windows location | \\rvc-nas-05\sld
6 | Mentor_Mentee presentation
| File name | <Generation>_<Term>Presentation_<your_name>_<your_code>
<Generation>: xxG
<Tern>: FirstTerm, MidTerm, Final
| Content | 1) Introduction: purpose of training, some information about job
2) Training plan
3) Your current status
4) Achievement and Action items
5) Interactive Mentor and Mentee
| Refer to manager's comments | We had 1st presentation of 20G Mentor-Mentee for MCU Solution 2
group today. But, I stopped the all presentation and suggested to
re-do because the contents of all presentation was same, that is,
all contents showed very general, like Mentor provide document
and Mentee study it and report it.
I expected the presentation to show what you want to be (target, not
only skill level) and how you do in order to achieve your target. It must
be different from each people. Please think what you want to be first,
and think what skill you need and skill level in order to be what you want.
Please think and recheck your presentation.
7 | [ISO] Training plan and history
Each the end of year, we will prepare a "training plan" (company level) for next year and report "training history" of current year
Please follow below instruction:
| Training plan |  | Instruction of how to get document number and upload your training plan file to DMS
| Your <new_year> training plan is put at Documents/2. Controlled Documents/29_SLD/99_TRAINING/<new_year> |  | 1. Register your document number to "Document_List_TRAINING.xls" file (file location: Documents/2. Controlled Documents/29_SLD/99_TRAINING) Your number will be the number of latest entry plus 1. Please fill your number and upload the file to DMS again. 2. Create your training plan in <new_year> 3. Send the file to GrL to get approval 4. Upload approved file to DMS at Documents/2. Controlled Documents/29_SLD/99_TRAINING/<new_year> 5. Update "Document_List_TRAINING.xls" file again to fill your document information (created by, examiner, approver, ...)
| Training history |  | Instruction of how to get document number and upload your training history file to DMS
| Your <current_year> training history is put at Documents/4. Controlled Records/29_SLD/99_TRAINING/<current_year> |  | 1. Register your record number to "Training_record_master_list.xls" file (file location:Documents/4. Controlled Records/29_SLD/99_TRAINING) Your number will be the number of latest entry plus 1. Please fill your number and upload the file to DMS again. 2. Create your training history. This step is different from training plan. Training plan describe for 1 year, training history record accumulated every year. It means <current_year> training history record all training from <last_year> to <current_year>. <last_year> training history files may be deleted. 3. Send the file to GrL to get approval 4. Upload approved file to DMS at Documents/4. Controlled Records/29_SLD/99_TRAINING/<current_year> 5. Update "Training_record_master_list.xls" file again to fill your record information (created by, examiner, approver, ...)
8 | MBO setting
| 1) Login to | https://renesas.ehr.com/
| 2) Go to | My career -> Target Setting (MBO)
3) Setting for Goal
a) Add objective
* Objective: Your task
* Description: Your target for this task (what should you do, what is your expected)
* Measure/Process: Your result (what did you do, archive/un-archive)
b) Edit objective weighting
c) Submit your MBO

## PartTimeEng
Back ground |  | Period
Modeling's skill | Target | First week | Last week
Common
Working flow | * Understand working flow: + 4 phases: PPDR -> PDR -> IDR -> FDR + Documents/ input/ output of each phase | * Trainer: + Explain about working flow, input/ output of each phase * Trainee: + Investigate python/perl/cshell script | -
Hardware manual investigation | * Understand REQ * The way to get necessary information quickly * Technical knowledge: features of model, operations * Output: CFM | * Trainer: + Provide a HWM as a sample + Share hint points to get necessary information + Introduce about CFM file * Trainee: + Output: Report understanding about sample model + Use CFM file to confirm understanding
Risk/Issue management | * The skill to avoid missing in implementation * The skill to avoid misunderstanding * The skill to evaluate, find counter measure * Output: (ISM, Bug/Issue report)
Design role
Design Specification | * Show idea/ mind for design in INT file clearly * Output: INT (just simple chapter without technical knowledge) | - | * Trainer: + Introduce about INT + Asign creation with chapters: 2, 3, 4, 5.1, 6 * Trainee: + Make INT (just asigned chapters)
Coding | * SystemC, TLM 2.0, common library * Coding style, coding rule * Output: Source code |  | * Trainee: + Investigate using the "generate register IF tool", "generate command IF tool"
Code review | * Get experience to check code, trade code * Output: (Redmine, review minutes)
Verification role
Verification Specification | * Show idea/ mind for verification in VRF file clearly * Output: VRF (just simple chapter without technical knowledge), VRF-01 (just Registers and Handle Command sheets), INR | - | * Trainer: + Introduce about VRF, VRF-01, INR
Test items creation | * Know necessary test items: + Basic: registers, handle command + Feature: input/output port states, timing, reset, configure | - | * Trainee: + Investigate using the "generate TM tool"
Environment preparation | * SCHEAP and RESLX environment * Model connection | - | * Trainer: + Introduce about SCHEAP and RESLX environment
Verification component | * Create/configure test module | - | * Trainee: + Investigate test modules + Output: Simple test module
Functional debug | * Bug/ Issues detection * Bug trace * Solution to fix | * Trainee: (*) + Execute data and report results | -
Notes:
PPDR: Pre-Preliminary Design Review |  | (*) New members join at current debug phase of real model. So, they will do task in first week instead of second week
PDR: Preliminary Design Review
IDR: Internal Design Review
FDR: Final Design Review
REQ: Requirement file
CFM: Confirmation point management file
ISM: Issue management file
INT: Internal specification file
USR: User Manual file
VRF: Verification specification file
VRF-01: Checklist items file
INR: Internal Verification report
SCHEAP/RESLX environment = an unit test environment
TLM: Transaction Level Modeling

## FullTimeEng
Back ground |  | Period
Modeling's skill | Target | First 2 months | Next 4 months | Next 6 months | Next 6 months | Last 6 months
Common
Working flow | * Understand working flow: + 4 phases: PPDR -> PDR -> IDR -> FDR + Documents/ input/ output of each phase | Level 1 (F) | Level 2 | Level 3 | <- | <-
Hardware manual investigation | * Understand REQ * The way to get necessary information quickly * Technical knowledge: features of model, operations * Output: CFM | Level 1 (F) | Level 2 | Level 3 | <- | <-
Risk/Issue management | * The skill to avoid missing in implementation * The skill to avoid misunderstanding * The skill to evaluate, find counter measure * Output: (ISM, Bug/Issue report) | Level 1 (F) | <- | Level 1 (L) | <- | Level 2
Design role
Design Specification | * Show idea/ mind for design in INT file clearly * Output: INT, USR | Level 1 (F) | <- | Level 2 | <- | Level 3
Coding | * SystemC, TLM 2.0, common library * Coding style, coding rule * Output: Source code | Level 1 (F) | <- | Level 1 (L) | Level 2 | Level 3
Code review | * Get experience to check code, trade code * Output: (Redmine, review minutes) | Level 1 (F) | <- | Level 1 (L) | <- | Level 3
Verification role
Verification Specification | * Show idea/ mind for verification in VRF file clearly * Output: VRF, VRF-01, INR | Level 1 (F) | Level 1 (L) | Level 2 | <- | Level 3
Test items creation | * Know necessary test items: + Basic: registers, handle command + Feature: input/output port states, timing, reset, configure | Level 1 (F) | Level 1 (L) | <- | Level 2 | <-
Environment preparation | * SCHEAP and RESLX environment * Model connection | Level 1 (F) | Level 2 | <- | <- | Level 3
Verification component | * Create/configure test module | Level 1 (F) | Level 1 (L) | <- | Level 2 | Level 3
Functional debug | * Bug/ Issues detection * Bug trace * Solution to fix | Level 1 (F) | <- | Level 1 (L) | Level 2 | <-
Mentor's action |  | * Explain about working flow, input/ output of each phase. * Share experience about hardware investigation and using CFM file to confirm unclear points. * Introduce methodology to develop model. * Introduce about SCHEAP/RESLX environment, types of specification, SystemC sample code, transaction, ..., and generation tools. | * Assign verification task. * Confirm for mentee's investigate result. * Follow up mentee's schedule. * Support for issues if any. | * Assign task (as design or verification role). * Confirm for mentee's investigate result. * Follow up mentee's schedule. * Support for issues if any. | * Assign task. * Confirm for mentee's investigate result. * Follow up mentee's schedule. * Support for hard issues if any. | * Little support (hints) in complex cases
Mentee's action |  | * Create schedule based on working flow. * Investigate HWM and using CFM for confirming unclear points. * Create design and verification specification. * Investigate environment. * Using SystemC to implement source code. * Use Generation Tools. | * Investigate HWM and using CFM for confirming unclear points with customer. * Create verification documents (simple contents: Register, Ports, Parameter and Conmmand): reuse and modify. * Prepare verification environment. * Use Generation Tools. | * Investigate HWM and using CFM for confirming unclear points with customer. * Create new REQ, design and verification documents (simple contents: Register, Ports, Parameter and Conmmand) * Prepare verification environment. * Make source code. * Use Generation Tools. | * Try to do tasks follow working flow without support. | * Try to do tasks follow working flow without support.
Notes:
PPDR: Post-Preliminary Design Review |  | Level 1, Level 2, Level 3: levels of skill are defined by Renesas.
PDR: Preliminary Design Review |  | (F) = can work with full support
IDR: Internal Design Review |  | (L) = can work with little support
FDR: Final Design Review |  | "<-": No change
REQ: Requirement file
CFM: Confirmation point management file
ISM: Issue management file
INT: Internal specification file
USR: User Manual file
VRF: Verification specification file
VRF-01: Checklist items file
INR: Internal Verification report
SCHEAP/RESLX environment = an unit test environment
TLM: Transaction Level Modeling

## QA
Question List
1 | What is your image about System-Level Modeling in SystemC?
2 | List the phases in working flow and show the input/output of each phase.
3 | Let share your experience about HWM investigating: How can you get the overview of an IP (know the feature of IP) in short time?
4 | List of Design's tasks
5 | List of Verification's tasks
6 | How can connect a model into RESLX environment?

## Process
| Back ground |  | Period (May/B 2017 -> Apr/E 2019)
| Modeling's skill | Target | First 2 months | Next 4 months | Next 6 months | Next 6 months | Last 6 months
Common
T01 | Working flow | * Understand working flow: + 4 phases: PPDR -> PDR -> IDR -> FDR + Documents/ input/ output of each phase | * Task 01_01_01: Explain about working flow, input/ output of each phase + Input: \Common\03_Docs\02_Guidelines\ + Status: done (sharing meeting on May 09, 2017)
* Task 01_01_02: Explain about ISO procedure + Input: \Common\03_Docs\02_Guidelines\ISO_tip_SLD_201606.pptx + Status: done (sharing meeting on May 19, 2017)
* Task 01_01_03: QA01 + Input: Answer questions No.1 -> 6 in QA sheet + Output: 01_Report\QA01_<trainee name> file D/L: Jun 02, 2017 + Status: done
* Task 01_01_04: Weekly report (on Redmine) + Input: (Template of report) ipp\project\2017\rvc\201705_FullTime_Training\00_Management\WeeklyReport\WeeklyReport_template_Redmine.txt + Output: Status report on Redmine D/L: Every morning 9AM of Friday + Status: done (training using Redmine)
* Task 01_01_05: Make SCD (on Redmine) + Output: Upload SCD to Redmine + Status: T.B.D (training using Redmine)
* Task 01_01_06: Create project task (on Redmine) + Input: Follow "1" in Common sheet + Output: Create a new ticket to discuss about project + Status: T.B.D (training using Redmine)
* Task 01_01_07: Create [ISO] Training plan and history + Input: Follow "7" in Common sheet + Status: on going (training the instruction "7" in Common sheet)
* Task 01_01_08: MBO setting + Input: Follow "8" in Common sheet + Status: on going (training the instruction "8" in Common sheet)
T02 | Hardware manual investigation | * Understand REQ * The way to get necessary information quickly * Technical knowledge: features of model, operations * Output: CFM | * Task 02_01_01: Share experience about hardware investigation and using CFM file to confirm unclear points + Input: HWM & CFM (ECM model) + Output: 01_Report\Investigate_HWM_report_<trainee name> file D/L: May 10, 2017 (check) and May 15, 2017 (final) + Status: done (sharing meeting on May 10, 2017) | * Task 02_02_01: Investigate HWM + Target: # Register list, port list, feature list + Input: HWM + Output: CFM D/L: T.B.D | * Task 02_03_01: Investigate HWM + Target: # Command handler list: decide commands need to be supported + Input: HWM + Output: CFM D/L: T.B.D | * Task 02_04_01: Investigate HWM + Target: # Wave form for each feature + Input: HWM + Output: CFM D/L: T.B.D | * Task 02_05_01: Investigate HWM (completely) + Input: HWM + Output: CFM D/L: T.B.D
|  |  | * Task 02_01_02: Document review + Target: # Check output document: INT, VRF, VRF-01 to confirm understanding with others + Input: INT, VRF, VRF-01 of ECM model + Output: Task on Redmine D/L: Jun 13, 2017 | * Task 02_02_02: QA02a + Input: Answer questions No.3 in QA sheet + Output: 01_Report\QA02a_<trainee name> file D/L: T.B.D + Status: | * Task 02_03_02: QA02b + Input: Answer questions No.3 in QA sheet + Output: 01_Report\QA02b_<trainee name> file D/L: T.B.D + Status: | * Task 02_04_02: QA02c + Input: Answer questions No.3 in QA sheet + Output: 01_Report\QA02c_<trainee name> file D/L: T.B.D + Status: | * Task 02_05_02: QA02d + Input: Answer questions No.3 in QA sheet + Output: 01_Report\QA02d_<trainee name> file D/L: T.B.D + Status:
T03 | Risk/Issue management | * The skill to avoid missing in implementation * The skill to avoid misunderstanding * The skill to evaluate, find counter measure * Output: (ISM, Bug/Issue report) | - | * Task 03_02_01: 5-why analysis
Design role
T04 | Design Specification | * Show idea/ mind for design in INT file clearly * Output: INT, USR | -
T05 | Coding | * SystemC, TLM 2.0, common library * Coding style, coding rule * Output: Source code | * Task 05_01_01: How to use generation tools (commandIF, registerIF) + Input: - [DMS] Documents/1. General Documents/010_ENG/140_FrontEnd/Project/01_SLD/2_SLD_Project/Model_Documents/01_Project_Document_Management/00_COMMON/04_Common_doc/Command IF Generator - [DMS] Documents/1. General Documents/010_ENG/140_FrontEnd/Project/01_SLD/2_SLD_Project/Model_Documents/01_Project_Document_Management/00_COMMON/04_Common_doc/Register IF Generator + Status: done (On desk training) | * Task 05_02_01: Model interface + Target: # Create interface for model + Input: HWM + Output: Source code for interface (compiled) + Status: T.B.D | * Task 05_03_01: Model interface + core (register) + Target: # Create interface + core for model + Input: HWM + Output: Source code for interface + core (compiled) + Status: T.B.D | * Task 05_04_01: Model interface + core (register + feature) + Target: # Create interface + core for model + Input: HWM + Output: Source code for interface + core (compiled) + Status: T.B.D | * Task 05_05_01: Model interface + core (completely) + Target: # Create interface + core for model + Input: HWM + Output: Source code for interface + core (compiled) + Status: T.B.D
* Task 05_01_02: How to use doxygen + Status: T.B.D
T06 | Code review | * Get experience to check code, trade code * Output: (Redmine, review minutes) | * Task 06_01_01: How to review code (reviewer may not be developers) + Input: ExperienceSharing_Modeling.pdf (slide 26 -> 29) + Status: T.B.D
* Task 06_01_02: How to use check1team + Status: T.B.D
Verification role
T07 | Verification Specification | * Show idea/ mind for verification in VRF file clearly * Output: VRF, VRF-01, INR | * Task 07_01_01: How to verify a model effectively + Input: ExperienceSharing_Modeling.pdf (slide 17 -> 22) + Status: done (sharing meeting on May 19, 2017)
T08 | Test items creation | * Know necessary test items: + Basic: registers, handle command + Feature: input/output port states, timing, reset, configure | * Task 08_01_01: Creating TM + Input: GenTMfromChecklist_v2014.08(GeneratingTM tool) + Output:TMs + Status: done (On desk training)
T09 | Environment preparation | * SCHEAP and RESLX environment * Model connection | * Task 09_01_01: Structure test environment + Target: # Using Git/CVS to clone data # Structure test environment (RESLX): connect IPs + Input: T.B.D => Duc-san + Output: environment which is compiled + Status: # Using Git/CVS to clone data => done (On desk training) # Structure test environment (RESLX): connect IPs => done (On desk training) | * Task 09_02_01: Structure test environment + Target: # Structure test environment (SCHEAP): connect IPs + Input: T.B.D + Output: environment which is compiled + Status: # Structure test environment (SCHEAP): connect IPs
|  |  | * Task 09_01_02: Structure test environment - RESLX (report) + Output: 01_Report\Investigate_ENV01_report_<trainee name> file D/L: Jun 23, 2017 (check) and Jun 30, 2017 (final) + Status: on going | * Task 09_02_02: Structure test environment - SCHEAP (report) + Output: 01_Report\Investigate_ENV02_report_<trainee name> file D/L: T.B.D (check) and T.B.D (final) + Status: on going
T10 | Verification component | * Create/configure test module | * Task 10_01_01: Configure test module + Target: # Update IF of test module + Output: Test module + Status: T.B.D
T11 | Functional debug | * Bug/ Issues detection * Bug trace * Solution to fix | * Task 11_01_01: How to use check coverage + Status: T.B.D
* Task 11_01_02: Confirm execution result for ECM model (E2x_FCC2) + Target: # Confirm failed TM and analyse failed cause + Input: ECM environment for E2x_FCC2 + Output: Report file, Task on Redmine D/L: Jun 16, 2017
| Mentor's action |  | * Explain about working flow, input/ output of each phase. * Share experience about hardware investigation and using CFM file to confirm unclear points. * Introduce methodology to develop model. * Introduce about SCHEAP/RESLX environment, types of specification, SystemC sample code, transaction, ..., and generation tools. | * Assign verification task. * Confirm for mentee's investigate result. * Follow up mentee's schedule. * Support for issues if any. | * Assign task (as design or verification role). * Confirm for mentee's investigate result. * Follow up mentee's schedule. * Support for issues if any. | * Assign task. * Confirm for mentee's investigate result. * Follow up mentee's schedule. * Support for hard issues if any. | * Little support (hints) in complex cases
| Mentee's action |  | * Create schedule based on working flow. * Investigate HWM and using CFM for confirming unclear points. * Create design and verification specification. * Investigate environment. * Using SystemC to implement source code. * Use Generation Tools. | * Investigate HWM and using CFM for confirming unclear points with customer. * Create verification documents (simple contents: Register, Ports, Parameter and Conmmand): reuse and modify. * Prepare verification environment. * Use Generation Tools. | * Investigate HWM and using CFM for confirming unclear points with customer. * Create new REQ, design and verification documents (simple contents: Register, Ports, Parameter and Conmmand) * Prepare verification environment. * Make source code. * Use Generation Tools. | * Try to do tasks follow working flow without support. | * Try to do tasks follow working flow without support.
Notes:
| PPDR: Post-Preliminary Design Review |  | Level 1, Level 2, Level 3: levels of skill are defined by Renesas.
| PDR: Preliminary Design Review |  | (F) = can work with full support
| IDR: Internal Design Review |  | (L) = can work with little support
| FDR: Final Design Review |  | "<-": No change
REQ: Requirement file
CFM: Confirmation point management file
ISM: Issue management file
INT: Internal specification file
USR: User Manual file
VRF: Verification specification file
VRF-01: Checklist items file
INR: Internal Verification report
SCHEAP/RESLX environment = an unit test environment
TLM: Transaction Level Modeling
New task
Finished task
Focussing task