## Slide 1
Mentor - Mentee Training Plan
MCU System Design Group
Mentor: Nghi Dang
Mentee: Quan Huynh
December 16, 2015 V1.0
Renesas Design Vietnam co., Ltd.

## Slide 2: Agenda
Introduction 3
Target and skill 5
Schedule 9
Action items 11
Detail plan 14

## Slide 3
Introduction

## Slide 4: Introduction mentor - mentee
Mentor
Name: Dang Huu Nghi
Gen: 08G
Code: 0535
Mentee
Name: Huynh Hong Quan
Gen: 22G
Code: 1595

## Slide 5
Target and Skill

## Slide 6: ROLE
+ Create verification item check list
+ Create test pattern for verification
+ Conduct verification of RTL
+ Evaluate verification result
+ Check specifications
+ Determine verification strategy
Functional Design
Functional Verification
+ Create module/chip design spec
+ Create LSI functional description
+ Create top level net list
+ Create timing budget
+ Determine strategies of evaluation and testing
70% work load
30% work load

## Slide 7: TARGEt After 2 year
Perform verification (main role ) without support from other.
Achieve level of functional verification: 2.67 (Main role).
Achieve level of functional design: 2.25 (Sub role).
Become trustworthy engineer.
Nov 2015
Nov 2016
Nov 2017
Level 1
Level 2
Level 3
This page is no need
Level 3 and 2.67 are not same

## Slide 8: Skill level
Main role : Engineer for Function verification level 2.67
Sub-role : Engineer for Functional design level 2.25

## Slide 9
Schedule

## Slide 10: Skill level
No. | Functional Verification | 15S | 16K | 16S | 17K
1 | Conduct functional verification of RTL. | 2 | 2 | 2 | 3
2 | Create test pattern for functional verification. | 1 | 2 | 3 | 3
3 | Evaluate functional verification result. | 2 | 2 | 2 | 3
4 | Create verification item list. | 1 | 2 | 3 | 3
5 | Check specifications. | 1 | 1 | 2 | 2
6 | Determine verification strategy. | 1 | 1 | 1 | 2
Average level |  | 1.33 | 1.67 | 2.17 | 2.67
No. | Functional Design | 15S | 16K | 16S | 16K
1 | Create top level netlist. | 2 | 2 | 3 | 3
2 | Modify and create LSI RTL descriptions. | 1 | 2 | 2 | 2
3 | Create timing budget. | 1 | 1 | 1 | 2
4 | Create module design specifications. | 1 | 1 | 2 | 2
Average level |  | 1.25 | 1.5 | 2 | 2.25
Where are they from?
Please check page 7 of
/shsv/mcsd/report/MentorMentee/Training Plan Review OJT Mentor Mentee En 20150213 v3.ppt
Please consider if it is reasonable
Reasonable?

## Slide 11
Action Items

## Slide 12: Action items (1/2)
Task name | What to do | 
 | Mentor | Mentee
Functional Verification | - Provide document & training: + Make checklist follow verification policy. + Conduct verification, check result. + Make plan. + Check Spec of module. | Define schedule of verification of assigned module. Judge pass/fail result of checked items. Create checklist, conduct verification, check result.
Functional Design | - Provide and training: + Create module specification. + Create RTL description & check. + RTL and verification environment. | Define schedule of design of assigned module. Make module spec, implement RTL, check RTL. - Report result to mentor.
This is very general
-> Do we need it?

## Slide 13: Action items (2/2)
Communication
method
Daily discussion
Review meeting
Email and Redmine
Doc and lab
Training method:
- Investigate and practice old projects to have the basic knowledge and main method of each task.
- On job training.
This title may not suitable -> Maybe “Training & Communication Method”

## Slide 14
DETAIL PLAN

## Slide 15: ACTIVITIES in 15S
Skills | How to do | 
 | Mentor | Mentee
Conduct functional verification of RTL (Level 2) | + Provide module/checklist/sample pattern of UT and HC environment. + Explain the structure of sim env and script for running simulation. + Guide to use verdi and vcs tools. | + Investigate verification environment structure, simulation option and execution flow. + Run simulation base on verification item list. + Judge log file, use verdi to analyze error.
Evaluate functional verification result (Level 2) | + Provide doc of coverage test. + Explain about function/role of coverage test in verification. + Evaluate the result with mentee. | + Run coverage test and improve the code coverage grade. + Modify to correct pattern and assertion. + Confirm the pass/fail result of simulation.
Create top level netlist (Level 2) | + Provide spec and RTL of SYSCTRL module. + Introduce usage of checker tools, timing violation report, methods to solve timing violation. | + Investigate constraints between data and clock, check timing violation report. + Do synthesize the RTL of module to gate netlist.

## Slide 16: ACTIVITIES in 15S
No. | Functional Verification | 15S |  |  |  | 
 |  | Nov | Dec | Jan | Feb | Mar
1 | Conduct functional verification of RTL. |  |  |  |  | 2
2 | Create test pattern for functional verification. |  |  |  |  | 1
3 | Evaluate functional verification result. |  |  |  |  | 2
4 | Create verification item list. |  |  |  |  | 1
5 | Check specifications. |  |  |  |  | 1
6 | Determine verification strategy. |  |  |  |  | 1
Average level |  | 1.33 |  |  |  | 
No. | Functional Design | Nov | Dec | Jan | Feb | Mar
1 | Create top level netlist. |  |  |  |  | 2
2 | Modify and create LSI RTL descriptions. |  |  |  |  | 1
3 | Create timing budget |  |  |  |  | 1
4 | Create module design specifications. |  |  |  |  | 1
Average level |  | 1.25 |  |  |  | 
Focus on: Functional verification skills
  Conduct functional verification of RTL reach level 2.
  Evaluate functional verification result reach level 2.
What is meaning of Nov/Dec….?

## Slide 17: ACTIVITIES in 16K
Skills | How to do | 
 | Mentor | Mentee
Conduct functional verification of RTL (Level 2) | + Provide verification plan. + Provide verification item list. | + Solve all errors/warnings during running simulation. + Confirm consistency for checked item between checklist and specification .
Create test patterns for functional verification (Level 2) | + Introduce over view of pattern structure. + Guide to write test patterns and run compile test pattern. | + Create sample test patterns for UT and HC by verilog or assembly. + Concern with mentor for difficult checked item.
Create timing budget (Level 2) | + Provide doc of timing design. + Guide to adjust the input/output timing in design. | + Understand concept of timing design such as synchronous and asynchronous. + Modify the input/output timing and run synthesis trial.

## Slide 18: ACTIVITIES in 16K
No. | Functional Verification | 16K |  |  |  |  | 
 |  | Apr | May | Jun | Jul | Aug | Sep
1 | Conduct functional verification of RTL. |  |  |  |  |  | 2
2 | Create test pattern for functional verification. |  |  |  |  |  | 2
3 | Evaluate functional verification result. |  |  |  |  |  | 2
4 | Create verification item list. |  |  |  |  |  | 2
5 | Check specifications. |  |  |  |  |  | 1
6 | Determine verification strategy. |  |  |  |  |  | 1
Average level |  | 1.67 |  |  |  |  | 
No. | Functional Design | Apr | May | Jun | Jul | Aug | Sep
1 | Create top level netlist. |  |  |  |  |  | 2
2 | Modify and create LSI RTL descriptions. |  |  |  |  |  | 2
3 | Create timing budget |  |  |  |  |  | 1
4 | Create module design specifications. |  |  |  |  |  | 1
Average level |  | 1.5 |  |  |  |  | 
Hand both: Functional verification skills & Functional design skills
  Create test pattern for functional verification reach level 2.
  Create verification item list reach level 2.
  Modify and create LSI RTL descriptions reach level 2.

## Slide 19: ACTIVITIES in 16S
Skills | How to do | 
 | Mentor | Mentee
Create test patterns (Level 3) | + Get information about difficulties Mentee when create patterns, assertion and show points need to improve. + Guide to make verification plan. | + Write the test pattern in verilog and assembly. + Solve the errors/warnings during compile test pattern.
Create verification item list (Level 2) | + Provide verification item list. + Guide to verification method, how to create verification Item list. | + Investigate the module specification. + Pick up the checked item from specification to checklist .
Check specification (Level 2) | + Provide spec before and after changing. + Review result of mentee. | + Investigate the specification of correlated module. + Conduct verification for correlated modules. + Evaluate verification result.

## Slide 20: ACTIVITIES in 16S
Skills | How to do | 
 | Mentor | Mentee
Evaluate functional verification (Level 3) | + Provide verification plan. + Guide to make verification plan. | + Decide to pick up the checked items from specification. + Evaluate verification result.
Create module design specifications (Level 2) | + Provide requirement spec, an sample spec, point out necessary content in detail spec. + Explain function/role of checker tools. | + Make detail block diagram of module. + Make state transition diagram of module. + Make design review with mentor.
Create top level netlist (Level 3) | +Discuss with Mentee about change points of the configuration of environment. +Evaluate the output of gate netlist and checker reports from Mentee. | + Create gate netlist by using synthesis tool . + Solve errors/warnings during synthesis report. + Make and confirm errors/warnings in report.

## Slide 21: ACTIVITIES in 16S
No. | Functional Verification | 16S |  |  |  |  | 
 |  | Oct | Nov | Dec | Jan | Feb | Mar
1 | Conduct functional verification of RTL. |  |  |  |  |  | 2
2 | Create test pattern for functional verification. |  |  |  |  |  | 3
3 | Evaluate functional verification result. |  |  |  |  |  | 2
4 | Create verification item list. |  |  |  |  |  | 3
5 | Check specifications. |  |  |  |  |  | 1
6 | Determine verification strategy. |  |  |  |  |  | 1
Average level |  | 2.17 |  |  |  |  | 
No. | Functional Design | Oct | Nov | Dec | Jan | Feb | Mar
1 | Create top level netlist. |  |  |  |  |  | 3
2 | Modify and create LSI RTL descriptions. |  |  |  |  |  | 2
3 | Create timing budget |  |  |  |  |  | 1
4 | Create module design specifications. |  |  |  |  |  | 2
Average level |  | 2 |  |  |  |  | 
Hand both: Functional verification skills & Functional design skills
  Create test pattern for functional verification reach level 3.
  Create verification item list reach level 3.
  Create top level netlist reach level 3.

## Slide 22: ACTIVITIES in 17K
Skills | How to do | 
 | Mentor | Mentee
Create verification item list (Level 3) | + Summarize issues can face when create verification item list. + Guide to make verification list. | + Do judgment for new verification items list. + Create verification item list from specification.
Determine verification strategy (Level 2) | + Training for create strategy fro verification based on requirement for each milestone. + Guide to make the bug budget. | + Check the product spec and list necessary modification points. + Determine scenario and method of verification. + Make detail verification plan.
Create LSI RTL description (Level 2) | + Provide detail spec; RTL coding policy manual of RTL checker tools. + Provide RTL. | + Investigate the module spec. + Create functional description and module connection.
Create timing budget (Level 3) | + Provide doc of timing design. + Explain about timing design. + Review result of mentee. | + Solve timing violation during synthesis. + Describe timing constraint for module levels. + Evaluate the timing constraint without support.

## Slide 23: ACTIVITIES in 17K
No. | Functional Verification | 16S |  |  |  |  | 
 |  | Apr | May | Jun | Jul | Aug | Sep
1 | Conduct functional verification of RTL. |  |  |  |  |  | 3
2 | Create test pattern for functional verification. |  |  |  |  |  | 3
3 | Evaluate functional verification result. |  |  |  |  |  | 3
4 | Create verification item list. |  |  |  |  |  | 3
5 | Check specifications. |  |  |  |  |  | 1
6 | Determine verification strategy. |  |  |  |  |  | 2
Average level |  | 2.67 |  |  |  |  | 
No. | Functional Design | Apr | May | Jun | Jul | Aug | Sep
1 | Create top level netlist. |  |  |  |  |  | 3
2 | Modify and create LSI RTL descriptions. |  |  |  |  |  | 2
3 | Create timing budget |  |  |  |  |  | 2
4 | Create module design specifications. |  |  |  |  |  | 2
Average level |  | 2.25 |  |  |  |  | 
Focus on: Functional verification skills
  Conduct functional verification of RTL reach level 3.
  Evaluate functional verification result reach level 3.

## Slide 24
www.renesas.com